Landmarks

Go-Live Plan

From Localhost Prototype to Production Web Application

April 2026

# Introduction

Landmarks is currently a localhost prototype built with HTML, Alpine.js, Tailwind CSS, and localStorage. This plan describes what needs to happen to turn it into a production web application, organized in three phases: Phase 1 covers the minimum work required for a public launch. Phase 2 covers features to build in the first 60 days post-launch to grow and retain users. Phase 3 covers ambitious future projects that should only be pursued once the core business is validated.

The migration path is: vanilla HTML/Alpine.js/localStorage → Next.js + Supabase + Resend + Vercel Cron. The localStorage data layer was designed so its API maps 1:1 to the planned Supabase schema, making the swap mechanical rather than architectural.

## Infrastructure Cost at Launch

| Service | Tier | Cost/Month |
| --- | --- | --- |
| Vercel (frontend + API) | Free → Pro at scale | $0–$20 |
| Supabase (DB + Auth) | Free → Pro at 500+ users | $0–$25 |
| Resend (email) | Free (3K/mo) → paid | $0–$20 |
| Domain | Any registrar | ~$1 (annualized) |
| Monitoring (Sentry) | Free tier | $0 |

Total at launch: effectively $0–$1/month. At 2,000 users: ~$45/month. At 5,000 users: ~$85/month. Revenue should exceed infrastructure costs from the first affiliate conversion.

# Phase 1: Launch Go-Live

Goal: Ship a publicly accessible product that real users can sign up for, enter contacts, and receive reminder emails with affiliate gift links. Estimated effort: 6–8 weekends (~50–70 hours).

## 1.1 Infrastructure Setup (Weekends 1–2)

- Set up Next.js project, deploy to Vercel, configure custom domain.

- Create Supabase project: provision database tables (profiles, contacts, events, reminder_log), enable Row-Level Security on all tables, configure Supabase Auth (email/password + Google OAuth).

- Create Resend account and verify sending domain. Configure SPF, DKIM, and DMARC records (start at p=quarantine, move to p=reject). Set up a dedicated sending subdomain (e.g., mail.landmarks.app) separate from the root domain.

- Register domain, set up DNS, configure SSL/TLS.

- Set up Sentry for error monitoring and alerting.

## 1.2 Core Application Migration (Weekends 2–4)

- Migrate all Store.js functions to Supabase client calls. The interface is designed to map 1:1, so this is a mechanical swap, not a redesign.

- Build signup/login flow with Supabase Auth (email/password + Google OAuth). Replace plaintext localStorage passwords with bcrypt + sessions.

- Extract duplicated page components (sidebar nav, auth guards, signOut, initials computation, mobile sidebar pattern) into shared Next.js components and hooks.

- Extract duplicated CSS (sidebar-link, badge styles, gradient-text) into a shared stylesheet or Tailwind config.

- Implement server-side input validation and sanitization for all user inputs before database insertion.

- Build error boundaries and user-facing error states for Store call failures.

## 1.3 Reminder Engine (Weekends 3–4)

- Build the Vercel Cron job: runs daily, queries events table for upcoming events within each user’s reminder window, cross-references reminder_log to prevent duplicates, composes emails, sends via Resend, logs to reminder_log.

- Implement timezone-aware sending: capture timezone at signup (browser default, user-editable), store per user, schedule per user. A 7-day reminder landing at 3 AM local time is a reminder that dies in the overnight email pile.

- Handle edge cases: timezone math (EST vs UTC boundary), leap year (Feb 29 → Feb 28 in non-leap years), late signups (birthday 2 days away, first window is 7 days → send immediate heads-up), duplicate prevention via unique constraint on (event_id, reminder_type, year).

- Design and build the HTML email template. Subject line format: "Your mom Sarah’s birthday is in 7 days — here’s what to get her."

## 1.4 Gift Curation Engine (Weekends 4–5)

This is the single most important feature and the largest pre-launch investment. Replace the static GIFT_DATA lookup table with a scoring-based recommendation engine:

- Structured gift catalog: Replace hardcoded gift-data.js with a gift_catalog table. Each item gets name, partner_id, affiliate_url, price_tier (under_25, 25_50, 50_100, over_100), 2–4 tags from a controlled vocabulary (~25 tags), relationship-affinity scores, event-type-affinity scores, seasonality flags, and a safe-default boolean. 100–200 well-tagged items at launch.

- Keyword-to-tag parser: A keyword_tags reference table (~150–200 entries) maps common words from the contact notes field to catalog tags via case-insensitive substring matching. Negation patterns (no/not/don’t/hate/allergic/never + keyword) trigger tag exclusions.

- Scoring function: At reminder-send time, score every active catalog item for the (user, contact, event) tuple. Weights: category_match ×5, tag_match ×3, relationship_affinity ×2, click_history ×4, price_match ×2, seasonality ×1, minus repeat_penalty ×10 and negative_tag ×1000. Pick top 3–4 items with diversity constraint (span 2–3 different tags).

- Behavioral data collection: click_events table, gift_feedback table (post-purchase thumbs up/down), and shown_items JSONB column on reminder_log to capture negative signal. This data tunes scoring weights automatically over time.

## 1.5 Contact Import (Weekend 5)

- CSV upload with column-mapping UI for name, birthday, relationship, notes fields.

- vCard (.vcf) paste/upload: parse standard vCard format for name + birthday.

- Google Contacts OAuth sync (second priority after CSV/vCard, as it requires OAuth setup).

- Rate-limit and abuse prevention on imports: server-side row count cap, email-domain rate limits.

## 1.6 Affiliate Partner Onboarding (Ongoing, Weeks 1–6)

- Sign up for 6–8 affiliate programs across categories: flowers (1-800-Flowers, Bouqs), gift cards (Amazon Associates), gourmet food (Goldbelly, Harry & David), wine (Wine.com), experiences (Uncommon Goods), eco/handmade (Etsy affiliate), charitable donations.

- Add affiliate tracking parameters (UTM conventions) to all outbound links.

- Create a one-page partner pitch doc: audience profile, expected send volume, sample reminder email, UTM conventions, reporting preview.

- No single partner should exceed 30% of projected revenue.

## 1.7 Security & Compliance (Weekend 6)

- Enable Supabase storage encryption (on by default for Pro plans). Add column-level encryption for PII columns (contacts.first_name, contacts.last_name, contacts.notes, events.custom_label) using pgcrypto or application-level encryption with per-user key.

- Test all RLS policies: verify users can only access their own data.

- Test account deletion flow: confirm full cascade delete of contacts → events → reminder_log.

- Test email deliverability: check spam scores with mail-tester.com. Monitor via Google Postmaster + Microsoft SNDS.

- Implement IP warmup schedule for sending domain (start low volume, ramp over 2–4 weeks).

- Finalize privacy policy and terms of service. Key commitments: no data selling, no contact email collection, hard delete on request, GDPR/CCPA compliance.

## 1.8 Launch Prep & Soft Launch (Weekends 7–8)

- Build minimum conversion dashboard: reminder sent → email opened → link clicked → purchase confirmed, broken by partner, gift category, and reminder timing (7-day vs 3-day).

- Set explicit success metrics: 10% click-to-purchase baseline, 50%+ activation rate (signup → enters 3+ contacts in week one), 85% MoM retention for active users.

- Manual QA: run through full user journey, test edge cases, verify email rendering across Gmail, Outlook, Apple Mail.

- Prepare launch posts for Reddit (r/productivity, r/LifeProTips, r/startups), Twitter/X (finance community), and Product Hunt.

- Deploy self-hosted privacy-respecting analytics (Plausible or Umami). No Google Analytics, no third-party trackers.

- Soft launch to personal network first. Collect feedback, fix bugs, iterate.

# Phase 2: Post-Launch Growth (Months 1–3)

Goal: Improve retention, grow organically, and validate the revenue model. These features are cheap, compounding, and should be shipped in the first 60 days after launch.

## 2.1 Retention & Engagement

- Gift-history ledger: One extra table (gift_history), one extra line in reminder emails: "Last year you sent Sarah flowers from Bouqs for $72." Reduces decision fatigue, lifts repeat conversion, makes the product feel like it knows the user. Effort: 2–3 days.

- Email subject-line A/B testing: Two variants per reminder, automatic winner selection after ~200 sends. Free (no tooling cost beyond a column in the sends table). Over months, 10–20% CTR lift is realistic and compounds across every email. Effort: 2–3 days.

- Preference center and unsubscribe granularity: One-click unsubscribe per RFC 8058 (required by Gmail/Yahoo for bulk senders), plus a preference page to turn off digests without killing reminders, or pause a single contact. Protects sender reputation and prevents full-account abandonment. Effort: 2–3 days.

- Natural-language event entry: "Add Mike, March 12, loves hiking." A regex-based parser handles the 80% case (name + date + optional notes). Edge cases fall back to the standard form. One-time cost, no per-use expense. Effort: 2–3 days.

- Lapsed-user re-engagement drip: 3-email sequence at D+3, D+10, D+30 for users who sign up but add zero contacts. Reclaims a meaningful slice of them for pennies. Effort: 2 days.

## 2.2 Organic Growth Loops

- Lightweight shared gift idea: A link a user can send to one other person (partner, sibling) showing a single gift candidate. Not a full group-gifting product. The recipient sees the product and often signs up. Viral loop with zero paid marketing cost. Effort: 3–5 days.

- Referral program: "Invite a friend; if they sign up, you both get [a tangible but cheap reward: a free premium card, a donation in their name]." Free users inviting free users is the right shape for an affiliate business where marginal-user cost is near zero. This should become the primary acquisition channel. Effort: 3–5 days.

- SEO content: Target long-tail keywords: "birthday reminder service," "never forget a birthday," "automated gift reminders." Short blog posts about gift ideas by relationship type, occasion, and budget serve dual purposes: SEO traffic and gift recommendation authority.

## 2.3 Revenue Optimization

- Per-partner CTR/CVR reporting: Once there is a month of data, send partners a one-page report showing click-through and conversion rates. This is the lever that gets commission-rate bumps — partners pay more for traffic they know converts. Zero product-side work beyond the conversion dashboard from Phase 1. Effort: half a day per month.

- Sponsored gift placements (begin planning): At 3K–5K active users with proven email open/CTR rates, pitch existing affiliate partners on a sponsored hero slot: one featured gift at the top of each reminder email, priced on CPM ($3–8). This raises ARPU from $1.50–$2.50/year to $5–$8/year. Prepare a media kit showing audience demographics, send volume, and open/click rates.

# Phase 3: Ambitious Future Projects (Month 6+)

These projects should only be pursued once the core business is validated: the curation engine is producing measurably better click-through than static links, affiliate revenue covers infrastructure, and the organic growth flywheel is turning. Each represents a significant investment and introduces new complexity.

## 3.1 SMS Reminders (Premium Tier)

Offer an optional SMS notification for the 3-day reminder only, via Twilio ($0.008/message, ~6 cents per user per year). This is the first candidate for a premium tier ($2–3/month) that diversifies revenue away from pure affiliate. Keep it opt-in, single channel, one message type. Do not let this become a primary channel — email stays the default. Revisit at 5,000+ users.

## 3.2 Browser Extension for Instant Contact Capture

When a user is on a contact’s LinkedIn or Facebook profile, one click pre-fills name + photo + optional notes into a new Landmarks contact. Small surface area, massive reduction in friction for the "I should really add them" moment. Also works as a word-of-mouth demo.

## 3.3 Gift Save-for-Later (Gift CRM)

Allow users to paste a URL from any partner site as a gift idea attached to a contact. Builds a user-curated layer on top of algorithmic recommendations. Turns Landmarks into a gift CRM, not just a reminder tool. Low build cost (URL + contact_id + note) but shifts the product positioning.

## 3.4 Shared Accounts / Couples Mode

Let two users manage a combined contact list so both partners are reminded and coordinated on gifts. Prevents the "we both sent Mom flowers" problem. Architecturally requires shared ownership on contacts, which is a non-trivial schema change, but the demand signal from couples will be strong.

## 3.5 Collaborative Filtering for Cold-Start Contacts

At 1,000+ users with purchase data, a simple collaborative filter (cosine similarity on user-item click matrices) can supplement the rule-based scoring engine for contacts with no click history. This is the point where the data flywheel becomes a genuine moat. Do not build before that threshold.

## 3.6 Automatic Gift Sending

Partner with a fulfillment service to let users pre-authorize a gift that auto-ships on the event date. This is the ultimate convenience play but introduces significant reputational risk (a bad auto-send goes viral) and requires robust error handling, confirmation flows, and customer support infrastructure. Pursue only if the manual curation engine has a strong track record.

## 3.7 Open-Source the Reminder Engine

The reminder scheduler and email templating are non-differentiating components. Open-sourcing them costs nothing, earns developer goodwill, and reinforces the privacy brand. Keep the curation engine closed. Evaluate at 2,000+ users.

# Revenue Milestones

| Month | Active Users | Revenue/Mo | ARR Run Rate | Notes |
| --- | --- | --- | --- | --- |
| 1 | 380 | $50 | $600 | Affiliate only; proving the funnel |
| 3 | 1,500 | $195 | $2,340 | First sponsor conversations start |
| 6 | 4,300 | $560 | $6,700 | Sponsors onboarded; ARPU rising |
| 12 | ~10,000 | $1,000+ | $12,000+ | Affiliate + sponsor; growth loops compounding |

The $20K ARR target is realistic at month 10–14 with affiliates only, or month 5–7 if sponsored placements are onboarded by month 3–4. The key variable is activation rate (signup → enters 3+ contacts). Target 50%+.

# Pre-Launch Checklist

- Domain registered and DNS configured

- Vercel account linked to GitHub repo

- Supabase project created: tables provisioned, RLS enabled, auth configured

- Resend account verified: sending domain authenticated, SPF/DKIM/DMARC records live

- 6+ affiliate programs signed up and tracking links configured

- Privacy policy and terms of service published

- All RLS policies tested and verified

- Account deletion flow tested (confirm full cascade delete)

- Email deliverability tested (spam scores checked via mail-tester.com)

- Error monitoring (Sentry) configured and alerting

- Conversion dashboard operational

- Landing page copy finalized

- Launch posts prepared for Reddit, Twitter/X, Product Hunt