LANDMARKS

Production Migration Plan

From Localhost Prototype to Next.js + Supabase + Resend + Vercel

| Date | April 2026 |
| --- | --- |
| Author | J (jamesohr@gmail.com) |
| Stack | Next.js 14+ (App Router) · Supabase · Resend · Vercel |
| Styling | Tailwind CSS + shadcn/ui |
| Package Manager | pnpm |
| Estimated Duration | 16–26 working days across 10 phases |

✅ PROGRESS UPDATE (April 2026): Phases 0–5 are COMPLETE. The Next.js app is deployed on Vercel with auto-deploy from GitHub. Supabase is provisioned with schema, RLS, and auth. Resend sends real emails via React Email templates. Three Vercel Cron jobs run daily (reminders, re-engagement) and monthly (digest). Phases 6–9 remain: gift recommendation engine, admin panel, marketing pages, testing/polish/go-live. Individual task statuses within completed phases may still show “Not started” below — disregard those; the phases are done. See CLAUDE.md for current architecture and remaining work.

# Overview

This document defines a phased plan for migrating Landmarks from a localhost prototype (vanilla HTML, Alpine.js, localStorage) to a production-ready application built on Next.js, Supabase, Resend, and Vercel. Each phase is designed to be independently deployable and testable, with clear deliverables and dependencies.

The prototype validated the UI/UX, data model, and email design. The Store API in js/store.js was deliberately designed so its interface maps 1:1 to the planned Supabase schema, making the data layer swap mechanical rather than architectural. The visual design (Tailwind utility classes, brand palette, component patterns) carries over directly.

| ⚠ | Key Architecture Decision This is a full rewrite into Next.js App Router, not an incremental migration. Each page is rebuilt as a proper React component with server-side data fetching, shared layouts, and real database persistence. The prototype’s page-per-file pattern maps naturally to Next.js’s file-based routing. |
| --- | --- |

## Phase Dependency Map

Phases are mostly sequential, but Phase 8 (Marketing Pages) can run in parallel with Phases 3–7 since it has no data dependencies beyond the base layout.

| Phase | Name | Duration | Depends On |
| --- | --- | --- | --- |
| Phase 0 | Project Scaffolding & Infrastructure | 1–2 days | — |
| Phase 1 | Database Schema & Row-Level Security | 1–2 days | Phase 0 |
| Phase 2 | Authentication (Email/Password + Google OAuth) | 2–3 days | Phase 1 |
| Phase 3 | Core App Pages: Dashboard, Contacts, Contact Detail | 3–4 days | Phase 2 |
| Phase 4 | Onboarding & Settings | 2–3 days | Phase 3 |
| Phase 5 | Email Delivery: Resend + Vercel Cron | 2–3 days | Phase 4 |
| Phase 6 | Gift Catalog & Recommendation Engine | 2–3 days | Phase 5 |
| Phase 7 | Admin Panel | 2–3 days | Phase 6 |
| Phase 8 | Marketing Pages & Public Routes | 1–2 days | Phase 0 |
| Phase 9 | Testing, Polish & Launch | 2–3 days | Phase 8 |

Total estimated effort: 16–26 working days (approximately 3–5 weeks for a solo developer, faster with parallel work on Phase 8).

Phase 0: Project Scaffolding & Infrastructure

Estimated duration: 1–2 days

Initialize the Next.js project, configure dev tooling, set up Supabase and Vercel projects, and establish the folder structure and shared utilities that every subsequent phase depends on.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Initialize Next.js 14+ with App Router via create-next-app | Dev | Critical | Not started |
| Configure pnpm as package manager with pnpm-workspace.yaml if needed | Dev | Critical | Not started |
| Install and configure Tailwind CSS v3 + PostCSS | Dev | Critical | Not started |
| Install and initialize shadcn/ui (components.json, base components: Button, Input, Label, Card, Tabs, Dialog, DropdownMenu, Badge, Toast, Avatar) | Dev | Critical | Not started |
| Create Supabase project (dashboard.supabase.com), note project URL and anon key | Dev | Critical | Not started |
| Install @supabase/supabase-js and @supabase/ssr; create lib/supabase/client.ts (browser) and lib/supabase/server.ts (server components / route handlers) | Dev | Critical | Not started |
| Create .env.local with NEXT_PUBLIC_SUPABASE_URL, NEXT_PUBLIC_SUPABASE_ANON_KEY, SUPABASE_SERVICE_ROLE_KEY | Dev | Critical | Not started |
| Set up Vercel project linked to GitHub repo; configure environment variables in Vercel dashboard | Dev | High | Not started |
| Create shared layout: app/layout.tsx (fonts, Tailwind, metadata), app/(marketing)/layout.tsx, app/(app)/layout.tsx (authenticated shell with sidebar) | Dev | High | Not started |
| Port brand color palette (brand-50 through brand-900) into tailwind.config.ts | Dev | High | Not started |
| Create lib/utils.ts with cn() helper, date formatters, and urgency helpers ported from Store.utils | Dev | High | Not started |
| Add ESLint + Prettier config for consistent code style | Dev | Medium | Not started |

### Deliverable

A running Next.js app on localhost:3000 with Tailwind + shadcn/ui, connected to an empty Supabase project, deployable to Vercel.

### Dependencies & Blockers

None — this is the foundation.

Phase 1: Database Schema & Row-Level Security

Estimated duration: 1–2 days

Define the full Postgres schema in Supabase, including tables, indexes, RLS policies, and seed data. The schema mirrors the localStorage model from store.js but adds proper types, constraints, and security.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Create profiles table: id (uuid, FK to auth.users), display_name, timezone, preferred_send_hour, reminder_days_before (int[]), default_gift_categories (text[]), monthly_digest_enabled, email prefs booleans, email_pause_until, zipcode, country, created_at, updated_at | Dev | Critical | Not started |
| Create contacts table: id (uuid), user_id (FK profiles), first_name, last_name, relationship (enum), gift_categories (text[]), gift_other, high_importance, budget_tier, notes, deleted_at (nullable timestamptz for soft-delete), created_at | Dev | Critical | Not started |
| Create events table: id (uuid), contact_id (FK contacts ON DELETE CASCADE), user_id (FK profiles), event_type (enum), event_label, month, day, year_started, one_time, event_year, high_importance, suppress_gifts, created_at | Dev | Critical | Not started |
| Create reminder_log table: id (uuid), user_id, contact_id, event_id, sent_at, days_before, email_status, gift_items (jsonb) | Dev | Critical | Not started |
| Create gift_catalog table: id (uuid), name, category, partner, affiliate_url, price_tier (enum: low/mid/high), relationship_affinities (text[]), event_type_affinities (text[]), tags (text[]), active (boolean), created_at, updated_at | Dev | Critical | Not started |
| Create shown_gifts table: id (uuid), user_id, contact_id, event_id, event_month, event_day, year, items (jsonb), created_at | Dev | High | Not started |
| Create conversion_events table: id (uuid), user_id, reminder_id, type (enum: sent/opened/clicked/purchased), partner, gift_category, commission, timestamp | Dev | High | Not started |
| Write RLS policies: users can only SELECT/INSERT/UPDATE/DELETE their own rows (user_id = auth.uid()). Admin role bypasses RLS via service_role key. | Dev | Critical | Not started |
| Add indexes: contacts(user_id, deleted_at), events(user_id), events(contact_id), reminder_log(user_id, sent_at), gift_catalog(category, active) | Dev | High | Not started |
| Create a Supabase SQL migration file (supabase/migrations/) for version-controlled schema | Dev | High | Not started |
| Write a seed script (supabase/seed.sql) that creates the demo user and sample contacts/events, replacing Store.seed.run() | Dev | Medium | Not started |
| Create a trigger function: auto-create a profiles row on auth.users INSERT (handles signup) | Dev | High | Not started |

### Deliverable

A fully defined Postgres schema in Supabase with RLS policies, indexes, and seed data. Verifiable via Supabase dashboard table editor.

### Dependencies & Blockers

Phase 0 must be complete (Supabase project exists).

Phase 2: Authentication (Email/Password + Google OAuth)

Estimated duration: 2–3 days

Implement the full authentication flow using Supabase Auth: sign-up, sign-in, sign-out, password recovery, password change, and Google OAuth. Build the auth UI pages and middleware for route protection.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Create app/(auth)/layout.tsx — centered card layout matching the prototype’s auth-bg gradient | Dev | Critical | Not started |
| Build app/(auth)/sign-in/page.tsx — email/password form, demo login shortcut, error handling, failed-attempt counter with recovery banner (port from auth.html) | Dev | Critical | Not started |
| Build app/(auth)/sign-up/page.tsx — name + email + password form, validation, redirect to onboarding | Dev | Critical | Not started |
| Build app/(auth)/recovery/page.tsx — 4-step wizard using Supabase Auth resetPasswordForEmail() and updateUser() (replaces simulated alert flow) | Dev | Critical | Not started |
| Configure Google OAuth in Supabase dashboard (Auth > Providers > Google); add Google Client ID and Secret from Google Cloud Console | Dev | High | Not started |
| Add Google sign-in button to sign-in and sign-up pages using supabase.auth.signInWithOAuth({ provider: ‘google’ }) | Dev | High | Not started |
| Create app/(auth)/callback/route.ts — handles OAuth redirect, exchanges code for session | Dev | High | Not started |
| Create middleware.ts at project root — check Supabase session on every request, redirect unauthenticated users to /sign-in, redirect authenticated users away from auth pages | Dev | Critical | Not started |
| Build a useUser() hook or server helper that provides the current user + profile across all authenticated pages | Dev | High | Not started |
| Build sign-out action (server action or API route) that calls supabase.auth.signOut() and redirects to landing page | Dev | High | Not started |
| Test: full sign-up → onboarding → dashboard → sign-out → sign-in flow end-to-end | QA | Critical | Not started |

### Deliverable

Working auth system: users can sign up, sign in (email or Google), recover passwords via real email, and are protected by middleware on all /app routes.

### Dependencies & Blockers

Phase 1 (profiles table + trigger must exist for sign-up to work).

Phase 3: Core App Pages: Dashboard, Contacts, Contact Detail

Estimated duration: 3–4 days

Port the three most-used pages from the prototype into Next.js server and client components. Extract the shared sidebar, navigation, and layout into reusable components.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Build components/app-sidebar.tsx — shared sidebar with nav links, user avatar/initials, sign-out button. Responsive: collapses behind hamburger below md breakpoint. Single source of truth (replaces 5 copies). | Dev | Critical | Not started |
| Build app/(app)/layout.tsx — flex layout with AppSidebar + main content area, auth guard via server component | Dev | Critical | Not started |
| Build app/(app)/dashboard/page.tsx — upcoming reminders list (server component fetching from Supabase), stat cards (contacts, events, urgent count), urgency badges with color coding | Dev | Critical | Not started |
| Create lib/queries/reminders.ts — port the reminder date math from Store.reminders.upcoming() to a server-side function querying Supabase | Dev | Critical | Not started |
| Build app/(app)/contacts/page.tsx — contact list with search, relationship filter, high-importance flag, add/edit/delete modals using shadcn Dialog | Dev | Critical | Not started |
| Create server actions: createContact, updateContact, trashContact, restoreContact, permanentDeleteContact in lib/actions/contacts.ts | Dev | Critical | Not started |
| Build app/(app)/contacts/[id]/page.tsx — single contact detail, event list, add/edit/delete event forms, shown-gift history section | Dev | Critical | Not started |
| Create server actions: createEvent, updateEvent, deleteEvent in lib/actions/events.ts | Dev | High | Not started |
| Build components/urgency-badge.tsx — shared badge component using the 0–3/4–7/8+ day thresholds | Dev | Medium | Not started |
| Port privacy messaging: “We never contact the people you add” on contacts page, “Your data is yours” on dashboard | Dev | Medium | Not started |

### Deliverable

Dashboard, contacts list, and contact detail pages fully functional with real Supabase data. Shared sidebar component eliminates all duplication.

### Dependencies & Blockers

Phase 2 (auth + middleware must be working so pages can query user-scoped data).

Phase 4: Onboarding & Settings

Estimated duration: 2–3 days

Build the post-signup onboarding wizard and the full settings page with its three tabs (General, Password, Recycling Bin). Port all preference management to Supabase.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Build app/(app)/onboarding/page.tsx — 4-step guided setup (welcome, add first contact + events, gift preferences, done). Server actions save to Supabase. Redirect to dashboard on completion. | Dev | Critical | Not started |
| Build app/(app)/settings/page.tsx with Tabs component (shadcn): General, Password, Recycling Bin | Dev | Critical | Not started |
| General tab: profile form (name, email disabled, ZIP, country, timezone), reminder timing chip picker, send hour dropdown, email preference toggles with pause, calendar feed, default gift preferences grid, data export, account deletion | Dev | Critical | Not started |
| Password tab: current password + new password + confirm, server action calling supabase.auth.updateUser({ password }) | Dev | High | Not started |
| Recycling Bin tab: list trashed contacts with avatars, countdown badges, restore/permanent-delete actions. Empty state with icon. | Dev | High | Not started |
| Create server action: updateProfile in lib/actions/profile.ts — writes to profiles table | Dev | Critical | Not started |
| Create server action: exportData — generates CSV from contacts + events, returns as downloadable file | Dev | Medium | Not started |
| Create server action: deleteAccount — cascading delete of all user data + Supabase auth.admin.deleteUser() | Dev | High | Not started |
| Port calendar feed: lib/calendar.ts with generateICS() function, download route at app/api/calendar/[userId]/route.ts returning text/calendar | Dev | Medium | Not started |
| Create lib/queries/contacts.ts — listTrashed() with days_left calculation, purgeExpired() called on settings load | Dev | High | Not started |

### Deliverable

New users see a guided onboarding flow. Settings page has all three tabs fully functional with real persistence.

### Dependencies & Blockers

Phase 3 (contact/event server actions are reused in onboarding).

Phase 5: Email Delivery: Resend + Vercel Cron

Estimated duration: 2–3 days

Wire up real email sending via Resend. Build the cron job that checks for due reminders daily and dispatches emails. Port email templates from the prototype’s email-preview.html into React Email components.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Create a Resend account (resend.com), generate API key, add RESEND_API_KEY to .env.local and Vercel env vars | Dev | Critical | Not started |
| Install resend and @react-email/components packages | Dev | Critical | Not started |
| Build emails/reminder.tsx — React Email component for the reminder email (contact name, event type, date, gift suggestions, affiliate links, shown-gift history line). Port layout from email-preview.html. | Dev | Critical | Not started |
| Build emails/digest.tsx — monthly digest email (list of upcoming events for next 30 days, only sent when events exist) | Dev | High | Not started |
| Build emails/reengagement.tsx — three drip templates (D+3 import nudge, D+10 sample reminder, D+30 concierge) ported from Store.reengagement | Dev | Medium | Not started |
| Create lib/email.ts — sendEmail() wrapper with env flag: if RESEND_API_KEY is set, send via Resend; otherwise console.log the email payload | Dev | Critical | Not started |
| Build app/api/cron/reminders/route.ts — GET handler (secured by CRON_SECRET header): query all users, compute due reminders per user’s timezone and send-hour preference, send emails, log to reminder_log table | Dev | Critical | Not started |
| Add vercel.json cron config: trigger /api/cron/reminders every hour (to respect per-user send hours across timezones) | Dev | Critical | Not started |
| Build app/api/cron/digest/route.ts — runs on the 1st of each month, sends digest to users with monthly_digest_enabled and upcoming events | Dev | High | Not started |
| Port email-config.js DNS documentation into a setup guide (SPF, DKIM, DMARC records for the domain once purchased) | Dev | Medium | Not started |
| Build app/(app)/email-preview/page.tsx — dev tool to preview email templates with sample data (port from email-preview.html) | Dev | Medium | Not started |
| Test: manually trigger the cron route via curl, verify email arrives in Resend test mode | QA | Critical | Not started |

### Deliverable

Reminder emails are sent automatically on schedule via Vercel Cron + Resend. Email templates match the prototype design. Digest and re-engagement flows are functional.

### Dependencies & Blockers

Phase 4 (user preferences like send_hour, reminder_days_before, and email toggles must be queryable).

Phase 6: Gift Catalog & Recommendation Engine

Estimated duration: 2–3 days

Populate the gift_catalog Supabase table and build the deterministic weighted scoring function that selects gift items per reminder. This is the single most important feature gap from the prototype.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Populate gift_catalog table with initial data: migrate items from gift-data.js + GIFT_DATA_LASTMINUTE, add tags, relationship_affinities, event_type_affinities, and price_tier to each item | Dev | Critical | Not started |
| Build lib/gifts/score.ts — deterministic weighted scoring function: inputs are contact (relationship, gift_categories, budget_tier), event (type, suppress_gifts), and profile (default_gift_categories). Scores each catalog item and returns top N. | Dev | Critical | Not started |
| Scoring weights: category match (40%), relationship affinity (25%), event type affinity (20%), price tier match (15%). Zero per-query cost — no LLM, no external API. | Dev | Critical | Not started |
| Add deduplication against shown_gifts: if an item was shown for the same contact+event last year, penalize its score so the user sees fresh suggestions | Dev | High | Not started |
| Respect suppress_gifts flag: if event has suppress_gifts=true, skip gift selection entirely and use the warm gift-free message template | Dev | High | Not started |
| Handle last-minute gifts: if days_until <= 3, prefer items from the last-minute catalog (digital gift cards, e-experiences, same-day delivery partners) | Dev | High | Not started |
| Integrate into reminder email flow: cron route calls scoreGifts() for each due reminder, passes results to the email template, and logs to shown_gifts | Dev | Critical | Not started |
| Write unit tests for the scoring function: verify category weighting, deduplication, suppress_gifts, last-minute logic | Dev | High | Not started |

### Deliverable

Every reminder email contains personalized, scored gift suggestions based on the contact’s preferences, with deduplication against past suggestions. No per-query cost.

### Dependencies & Blockers

Phase 5 (email templates + cron route must exist to integrate gift scoring into the send flow).

Phase 7: Admin Panel

Estimated duration: 2–3 days

Build the admin dashboard as a protected route group within the same Next.js app. Port the conversion funnel analytics and email queue with gift override capability.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Add is_admin boolean column to profiles table (default false). Set to true for the admin user. | Dev | Critical | Not started |
| Create app/(admin)/layout.tsx — admin shell with role check: query profile, redirect non-admins to dashboard. Separate sidebar with admin nav links. | Dev | Critical | Not started |
| Build app/(admin)/admin/page.tsx — analytics tab: KPI cards (emails sent, open rate, click rate, revenue), funnel visualization, partner/category breakdowns, daily trend chart. Data from conversion_events table. | Dev | High | Not started |
| Build app/(admin)/admin/queue/page.tsx — email queue tab: list pending reminder emails for next 7 days across all users, with gift override capability (select alternate gift items from catalog) | Dev | High | Not started |
| Create server actions for admin: getConversionMetrics, getBreakdown, getTimeSeries, getPendingEmails, setGiftOverride, removeGiftOverride | Dev | High | Not started |
| Add gift_overrides table: key (composite of user_id, event_id, days_before), gifts (jsonb), created_by (admin user_id), created_at. Cron route checks for overrides before using auto-scored gifts. | Dev | High | Not started |
| Port deliverability checklist from admin.html (SPF, DKIM, DMARC, bounce rate, complaint rate) as a status card | Dev | Medium | Not started |
| Add admin gift catalog management page: list/add/edit/deactivate gift items in the gift_catalog table | Dev | Medium | Not started |

### Deliverable

Admin users can view conversion analytics, preview the email queue, override gift selections, and manage the gift catalog — all within the same deployed app.

### Dependencies & Blockers

Phase 6 (gift scoring + catalog table must exist for queue and overrides to work).

Phase 8: Marketing Pages & Public Routes

Estimated duration: 1–2 days

Port the marketing and legal pages (landing, about, privacy, terms, contact form) into the Next.js app under the (marketing) route group. These are public, unauthenticated pages.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Build app/(marketing)/page.tsx — landing page: hero, feature blocks, privacy promise section (3 cards), “how we make money” copy, trust badges, CTA, cookie consent banner | Dev | High | Not started |
| Build app/(marketing)/about/page.tsx — origin story, privacy philosophy, business model transparency | Dev | Medium | Not started |
| Build app/(marketing)/privacy/page.tsx — static privacy policy | Dev | Medium | Not started |
| Build app/(marketing)/terms/page.tsx — static terms of service | Dev | Medium | Not started |
| Build app/(marketing)/contact/page.tsx — contact form with server action that sends via Resend to your support email | Dev | Medium | Not started |
| Create components/cookie-consent.tsx — cookie banner with customization modal, using a client-side cookie (not localStorage) | Dev | Low | Not started |
| Add OpenGraph meta tags and structured data for SEO on all public pages | Dev | Medium | Not started |

### Deliverable

All public-facing pages are live and SEO-ready. Contact form sends real emails.

### Dependencies & Blockers

Phase 0 (layout structure must exist). Can be done in parallel with Phases 3–7.

Phase 9: Testing, Polish & Launch

Estimated duration: 2–3 days

Comprehensive testing, bug fixes, performance optimization, and final deployment. This phase catches everything that slipped through individual phase testing.

### Tasks

| Task | Owner | Priority | Status |
| --- | --- | --- | --- |
| Write unit tests for core logic: reminder date math (timezone edge cases, DST transitions, leap years), gift scoring, urgency classification | Dev | Critical | Not started |
| Write integration tests for auth flow: sign-up → onboarding → dashboard → sign-out → sign-in → recovery | Dev | High | Not started |
| Write integration tests for data flow: create contact → add event → see on dashboard → trash → restore → permanent delete | Dev | High | Not started |
| Accessibility audit: keyboard navigation, screen reader labels, color contrast, focus management on modals | QA | High | Not started |
| Mobile responsive testing: verify sidebar collapse, touch targets, form usability on small screens | QA | High | Not started |
| Performance: add loading.tsx skeletons for each route, optimize Supabase queries (avoid N+1), verify Vercel Edge caching for public pages | Dev | High | Not started |
| Error handling: add error.tsx boundaries to each route group, handle Supabase errors gracefully with user-facing messages | Dev | High | Not started |
| Input sanitization: validate and sanitize all server action inputs (zod schemas recommended) | Dev | Critical | Not started |
| Purchase and configure custom domain: add to Vercel, set up DNS records, configure Resend domain verification (SPF, DKIM, DMARC) | Dev | High | Not started |
| Switch Resend from test mode to production: verify domain, update FROM address in email templates | Dev | Critical | Not started |
| Final deployment to Vercel production: verify env vars, test cron job, monitor first email sends | Dev | Critical | Not started |
| Update CLAUDE.md and README.md with production architecture, env var documentation, and deployment instructions | Dev | Medium | Not started |

### Deliverable

A production-ready Landmarks app deployed on Vercel, sending real emails, with automated tests and proper error handling.

### Dependencies & Blockers

All previous phases complete.

# Target File Structure

The following is the planned directory structure for the production Next.js app. It reflects the decisions made in this plan: App Router, shadcn/ui, server actions, and co-located route files.

landmarks-app/

├── app/

│   ├── layout.tsx                   Root layout (fonts, metadata, Tailwind)

│   ├── (marketing)/

│   │   ├── page.tsx                 Landing page

│   │   ├── about/page.tsx           About page

│   │   ├── privacy/page.tsx         Privacy policy

│   │   ├── terms/page.tsx           Terms of service

│   │   └── contact/page.tsx         Contact form

│   ├── (auth)/

│   │   ├── layout.tsx               Centered card layout

│   │   ├── sign-in/page.tsx         Sign in

│   │   ├── sign-up/page.tsx         Sign up

│   │   ├── recovery/page.tsx        Password recovery

│   │   └── callback/route.ts        OAuth callback

│   ├── (app)/

│   │   ├── layout.tsx               Authenticated shell + sidebar

│   │   ├── dashboard/page.tsx       Dashboard

│   │   ├── contacts/

│   │   │   ├── page.tsx             Contact list

│   │   │   └── [id]/page.tsx        Contact detail

│   │   ├── settings/page.tsx        Settings (3 tabs)

│   │   ├── onboarding/page.tsx      Post-signup setup

│   │   └── email-preview/page.tsx   Dev email preview

│   ├── (admin)/

│   │   ├── layout.tsx               Admin shell + role guard

│   │   └── admin/

│   │       ├── page.tsx             Analytics dashboard

│   │       └── queue/page.tsx       Email queue + overrides

│   └── api/

│       ├── cron/reminders/route.ts  Daily reminder job

│       ├── cron/digest/route.ts     Monthly digest job

│       └── calendar/[userId]/route.ts  ICS feed

├── components/

│   ├── ui/                          shadcn/ui components

│   ├── app-sidebar.tsx              Shared app sidebar

│   ├── urgency-badge.tsx            Urgency color badge

│   └── cookie-consent.tsx           Cookie banner

├── lib/

│   ├── supabase/client.ts           Browser Supabase client

│   ├── supabase/server.ts           Server Supabase client

│   ├── supabase/middleware.ts        Session refresh helper

│   ├── actions/contacts.ts          Contact server actions

│   ├── actions/events.ts            Event server actions

│   ├── actions/profile.ts           Profile server actions

│   ├── queries/reminders.ts         Reminder date math

│   ├── queries/contacts.ts          Contact queries (incl. trash)

│   ├── gifts/score.ts               Gift recommendation engine

│   ├── email.ts                     Resend wrapper

│   ├── calendar.ts                  ICS generation

│   └── utils.ts                     Shared helpers

├── emails/

│   ├── reminder.tsx                 Reminder email template

│   ├── digest.tsx                   Monthly digest template

│   └── reengagement.tsx             Drip email templates

├── supabase/

│   ├── migrations/                  SQL migration files

│   └── seed.sql                     Demo data seed

├── middleware.ts                     Auth middleware

├── tailwind.config.ts               Brand palette + extensions

├── vercel.json                       Cron config

└── .env.local                        Environment variables

## Environment Variables Reference

The following environment variables are required for the production deployment. All are configured in the Vercel dashboard and in .env.local for local development.

| Variable | Description |
| --- | --- |
| NEXT_PUBLIC_SUPABASE_URL | Supabase project URL (e.g. https://xxx.supabase.co) |
| NEXT_PUBLIC_SUPABASE_ANON_KEY | Supabase anonymous/public key for client-side auth |
| SUPABASE_SERVICE_ROLE_KEY | Supabase service role key for admin operations and cron jobs (server-only, never exposed to client) |
| RESEND_API_KEY | Resend API key for sending emails |
| CRON_SECRET | Shared secret to authenticate Vercel Cron requests to API routes |
| NEXT_PUBLIC_SITE_URL | Production URL (e.g. https://landmarks.app) for OAuth callbacks and email links |
| GOOGLE_CLIENT_ID | Google OAuth client ID (configured in Supabase dashboard, not in app code) |
| GOOGLE_CLIENT_SECRET | Google OAuth client secret (configured in Supabase dashboard) |